## Overview
EECE2140: Final Project Plan
Project | BMS Simulator (C++ management system)
Group | Group 07: Drew Bancroft, Kavi Bandara, Anthony Wang
Repository | https://github.com/K-Band/EECE2140_BMS_FinalProject
Last Updated | 2026-10-30
Member | Role | Classes Owned | Menu Tasks Owned | Led Iteration(s)
Drew Bancroft | Control/Safety Lead | Charger, SoCEstimator, EnergyTracker, Protection, Contactor | T3, T5, T6, T7 | 1
Kavi Bandara | Battery/Thermal Modelling Lead | Cell, Pack, OcvTable, ThermalModel | T1, T2 | 1
Anthony Wang | Simulation/UI Lead | Simulator, LoadProfile, Logger, EventLog, main.cpp | T4, T8, T9, T10, T0 | 0
Status | Menu Tasks | Classes
Done | 0 | 5
In Progress | 0 | 0
Stub | 0 | 0
Not started | 0 | 0
Not set yet | 11 | 8
Total | 11 | 13

## Tasks
Task ID | Task | Menu Option | Assignee | File | Function | Deliverable | Status | Target Milestone
T1 | Configure pack | 1 | Kavi | model_tasks.cpp | configurePack() | Prompts for cell count, capacity, internal resistance, and starting SOC, validates the input, and builds the pack. | Done | M1
T2 | Show thermal state | 2 | Kavi | model_tasks.cpp | showThermal() | Displays each cell's temperature, the ambient temperature, the I²R heat being generated, and the resulting internal resistance. | Done | M2
T3 | Run CC-CV charge cycle | 3 | Drew | control_tasks.cpp | chargeCycle() | Runs a CC-CV charge (constant current until a cell reaches 4.2 V, then constant voltage as current tapers, stopping at the cutoff current), with the live status line and a stop on any fault. | Done | M2
T4 | Run discharge (CC/pulsed/CSV) | 4 | Anthony | sim_tasks.cpp | dischargeCycle() | Lets the user choose a constant-current, pulsed, or CSV load profile, then discharges the pack until low SOC, undervoltage, or a fault ends the run. | Done | M2
T5 | Show SOC estimate vs. true | 5 | Drew | control_tasks.cpp | showSOC() | Displays the coulomb-counted SOC (from noisy, offset measured current) next to the true SOC, with the estimation error. | Done | M2
T6 | Show energy report | 6 | Drew | control_tasks.cpp | reportEnergy() | Displays Wh in, Wh out, round-trip efficiency, and cycle count. | Done | M2
T7 | Set protection thresholds / reset faults | 7 | Drew | control_tasks.cpp | setThresholds() | Shows and edits the WARNING and FAULT limits for each protection check, and resets a latched fault. | In Progress | M3
T8 | View event log | 8 | Anthony | sim_tasks.cpp | viewEvents() | Prints a timestamped list of run events: warnings, faults, contactor opening and closing, and charge/discharge start and stop. | In Progress | M3
T9 | Toggle CSV logging | 9 | Anthony | sim_tasks.cpp | toggleLog() | Turns per-timestep CSV logging on or off and sets the output file name. | Done | M1
T10 | Run demo scenario | 10 | Anthony | sim_tasks.cpp | runScenario() | Runs a canned demo scenario (normal charge, discharge, overcurrent fault, overtemperature fault, or CSV drive cycle) end to end. | In Progress | M3
T0 | Exit | 0 | Anthony | sim_tasks.cpp | exitProgram() | Ends the menu loop and closes any open log file before the program exits. | Done | M1

## Classes
Class | Owner | Header | Source | Test File | Status | Notes
Cell | Kavi | cell.h | cell.cpp | tests/test_model.cpp | Done | Merged in PR #5
Pack | Kavi | pack.h | pack.cpp | tests/test_model.cpp | Done | Merged in PR #5
OcvTable | Kavi | ocv_table.h | ocv_table.cpp | tests/test_model.cpp | Done | Merged in PR #5
ThermalModel | Kavi | thermal_model.h | thermal_model.cpp | tests/test_model.cpp | Done | Merged in PR #5
Charger | Drew | charger.h | charger.cpp | tests/test_control.cpp | Done | Merged in PR #6
SocEstimator | Drew | soc_estimator.h | soc_estimator.cpp | tests/test_control.cpp | Done | Merged in PR #6
EnergyTracker | Drew | energy_tracker.h | energy_tracker.cpp | tests/test_control.cpp | Done | Merged in PR #6
Protection | Drew | protection.h | protection.cpp | tests/test_control.cpp | Done | Merged in PR #6
Contactor | Drew | contactor.h | contactor.cpp | tests/test_control.cpp | Done | Merged in PR #6
Simulator | Anthony | simulator.h | simulator.cpp | tests/test_sim.cpp | Done | Merged in PR #8
LoadProfile | Anthony | load_profile.h | load_profile.cpp | tests/test_sim.cpp | Done | Merged in PR #8
Logger | Anthony | logger.h | logger.cpp | tests/test_sim.cpp | Done | Merged in PR #8
EventLog | Anthony | event_log.h | event_log.cpp | tests/test_sim.cpp | Done | Merged in PR #8

## Timeline
Milestone | Start | End | Code | Repo | Presentation | Report | Finish Line | Status | Change Since Iteration 1
M1: Foundation | 2026-10-11 | 2026-10-25 | Agree on architecture and class headers; set cell parameters and OCV table; implement Cell, Pack, timestep loop, constant-current discharge, and CSV logger; menu with a stub for every task. | Folder structure, Makefile, README skeleton; feature branches and pull requests with one reviewer each. | Start a running log of decisions and bugs. | — | ./bms runs a 1C discharge from full to empty, and the plotted voltage curve looks like a real discharge curve. | Done | Added: menu with a stub for every task, T0–T10 (Iteration 2 requirement).
M2: All models completed | 2026-10-25 | 2026-11-08 | Thermal model, CC-CV charger, pulsed and CSV load profiles, SOC estimation with sensor noise and offset, energy tracking with cycle count; check models against hand calculations. | Tests for OCV interpolation, CC-to-CV transition, and coulomb counting; document model parameters and assumptions. | Draft slide outline for all required topics. | — | A full charge-discharge cycle produces sensible voltage, temperature, and SOC-error plots. | In Progress | No change.
M3: UI, integration, feature freeze | 2026-11-08 | 2026-11-22 | Protection (thresholds, fault latching, contactor); live status line with ASCII SOC bar and event log; 4–5 canned demo scenarios; feature freeze on 11/22. | Final README: overview, features, build/run instructions, example output, architecture diagram. | Full slide draft, including the architecture diagram. | Outline the report; write the system design and model equation sections. | All scenarios run end to end from the menu, and faults trip and latch correctly. | N/A | The menu was built in M1, so UI work here is the live status line and event log. Protection and Contactor classes finished early (merged in PR #6).
M4: Final format, ready for presentation | 2026-11-22 | 2026-11-30 | Bug fixes only. | A teammate clones the repo fresh and follows the README; tag a v1.0 release. | Finalize slides, rehearse, and decide between a live or recorded demo. | Finish the report: results and future extensions. | Presentation delivered; repo tagged and submitted. | N/A | No change.

## Contributions
Iteration | Member | Planned (from previous iteration) | Completed | Pull Requests
Iteration 1 | Drew | — | Project timeline and milestones; team member objectives | #1
Iteration 1 | Kavi | — | Scope; team member objectives | #1
Iteration 1 | Anthony | — | Selected tech/tools; team member objectives | #3
Iteration 2 | Drew | Set up repo, Makefile, and .gitignore; draft Charger, SocEstimator, and Protection headers with fault thresholds | Implemented Charger, SocEstimator, EnergyTracker, Protection, and Contactor; wrote tests/test_control.cpp | #6
Iteration 2 | Kavi | Choose OCV-SOC table and cell chemistry; implement cell/pack terminal voltage | Selected OCV-SOC table and cell chemistry; implemented cell and pack models with terminal voltage calculations. | #5
Iteration 2 | Anthony | Build fixed timestep loop and CSV logger with a constant-current load so the cell can be plotted | Added task stubs for discharge cycle, event log, CSV logging, demo scenario, and exit. Implemented CSV logger, set up simulator timestep loop stub, and fixed build errors. | #8